## Development Tasks
S.No	Change Category	Change Type	Module	Page Link	Functionality	ID	Description	Priority	Severity	Impact	Assigned To	Effort Spent till Last working day(in hours)	Effort Spent today	Effort required to complete – next working day(s)	Total Effort	Start Date	Target Date	Status	Completed Date	Dependency	Remarks
1	N/A	Performance Improvement	Accounts	Allot Stock	Improve the Processing speed of the Allotment products in the Grid	N/A	Current js code is navigating all th products in the grid for each new(or edit) entry, which is taking unnecessary processing time.	Medium		Medium	Vinay	12	4		16	08/11/13	11/11/13	Completed	11/12/13
2	N/A	Performance Improvement	My Sales	Day Book	On load of Day Book, There are 6 Post call are going. We need to avoid those many no. of post calls and for every next unnecessary post call are going and we need to stop them too.	N/A	On load of Day Book, There are 6 Post call are going. We need to avoid those many no. of post calls and for every next unnecessary post call are going and we need to stop them too.	High		Major	Sudhakar	0				11/11/13		Completed	12/11/13
3	N/A	Performance Improvement	Dash Board	Reports	0000442: To Display All kinds of Reports(Product Wise,Sales Wise, and Customer wise) for all Products on Weekly & Monthly Bases on GUI	442	0000442: To Display All kinds of Reports(Product Wise,Sales Wise, and Customer wise) for all Products on Weekly & Monthly Bases on GUI				Swarupa
4	N/A	Build Issue	N/A	N/A	War file issue with tomcat project.	N/A	War file issue with tomcat project.				Sudhakar
5	N/A	Performance Improvement	My Sales	Sales Returns	Avoid unnecessary post calls of Sales Return on load and next button		Avoid unnecessary post calls of Sales Return on load and next button				Swarupa		8	1	8	12/11/13	12/11/13	Completed	12/11/13
6	N/A	New Requirement	Dash Board	Approvals	0000537: Product Wise Approval for Sales Return	537	0000537: Product Wise Approval for Sales Return				Swarupa	4	8			18/11/13		In Progress	20/11/13
7	N/A	New Requirement	Dash Board	Reports	0000530: Dynamic Reports Instead of Static Reports	530	0000530: Dynamic Reports Instead of Static Reports				Swarupa
8	N/A	Performance Improvement	My Sales	Delivery Note	Avoid unnecessary post calls of Delivery note on load and next button	N/A	Avoid unnecessary post calls of Delivery note on load and next button				Sudhakar		7	1	7	12/11/13	12/11/13	Completed	12/11/13
9	N/A	Performance Improvement			Separating the validation logic to common place instead of having in all the modules.	N/A	Separating the validation logic to common place instead of having in all the modules.	High	Major	Major	Ankit
10	N/A	Performance Improvement	Product	Import Products	Import functionality in the application	N/A	Import functionality in the application
11	N/A	Bug	My Sales	Sales Returns	Missing message while adding sales return	N/A	While Adding sales return with out inputs,It is not moving and not showing any message	Medium	Medium	Minor	Priyanka		1		1	12/11/13		Completed	12/11/13
12	N/A	Bug	My Sales	Day Book	Issue with vehicle fuel expenses update	N/A	When there is only one entry in vehicle fuel expenses,If we give more than ending reading while editing,It is accepting	High	Major	Minor	Priyanka		1		1	12/11/13		Completed	12/11/13
13	N/A	Performance Improvement	My Sales	Journal	Avoid unnecessary post calls of Journal.		Avoid unnecessary post calls of Journal.	High	Major	Major	Sudhakar		1		1	12/11/13	12/11/13	Completed	12/11/13
14	N/A	Bug	My Sales	Customer CR	Getting null value in vb_system_notification table for android. Need change this null to vbcustomer id or Requesting id.		Getting null value in vb_system_notification table for android. Need change this null to vbcustomer id or Requesting id.	High	Major	Major	Sudhakar		1		1	15/11/13	15/11/13	Completed	15/11/13
15	N/A	Customization & Enhancement	Product	Product-customer-cost	To give flexibility for the other management users to provide product customer cost		Currently we are restricting all the other management users except super management user to add cost for customers,need to remove the restriction	Medium	Medium	Medium	Vinay		3		3	11/16/13	11/16/13	Completed	11/16/13
16	N/A	New Requirement	Organization	Import-organization	To add new functionality to import group of organizations at a time		Currently we dont have functionality to bulk upload the organizations,i added new jsps and pagelinks for that purpose	Medium	Medium	Medium	Vinay		4		4	11/16/13	11/17/13	Progress
17	functional	Enhancement	Employee	Search Employee	Search Criteria to search based on One entry	534	.Search should be based on Name, irrespective of First Name, Last Name	Major	Major	medium	Priyanka	4			4	16/11/13	16/11/13	Completed	16/11/13
18	functional	Enhancement	Dashboard	System lookups	Product Categories to be included in System Lookups	533	System Lookups should have Product Categories	major	major	Major	Priyanka				10	18/11/13		Completed	19/11/13
19	UI	New Requirement	Module Bar		Change the Order of the Modules(Images) for VBooks App	540	.Need to Change the Order of the Modules(Images) for the Application	Major		minor	Priyanka		2			19/11/13		Progress
20	Functional	New Requirement	Employee	Emolyee Search	Reset the forgot password by super management user	539	Current System Does not Have the Option to Reset the Forget Password.Need to Have the Option by Super Management User.	Major	Medium	Medium	Priyanka	4			4	21./11/13		Completed	21/11/13

## V-books libs
activation.jar	camel-http4-2.9.0.jar	mail.jar	spring-webmvc-portlet.jar
activemq-all-5.1.0.jar	cglib-2.1.3.jar	mondrian-3.1.1.12687.jar	spring-webmvc-struts.jar
activemq-core-5.3.0.jar	cleanimports.jar	mysql-connector-java-5.1.5-bin.jar	standard-1.1.2.jar
activemq-pool-5.2.0.jar	commons-beanutils-1.8.0.jar	ojdbc14.jar	struts.jar
activemq-web-5.5.1.jar	commons-codec.jar	oscache-2.1.jar	swarmcache-1.0rc2.jar
ant-1.7.1.jar	commons-collections-3.2.1.jar	png-encoder-1.5.jar	syndiag2.jar
ant-antlr-1.6.5.jar	commons-collections-3.2.jar	poi-3.5-FINAL-20090928.jar	tomcat-jdbc-7.0.27.jar
ant-junit-1.6.5.jar	commons-dbcp-1.2.2.jar	project.jar	versioncheck.jar
ant-launcher-1.6.5.jar	commons-digester-1.7.jar	proxool-0.8.3.jar	xalan-2.6.0.jar
antlr-2.7.5.jar	commons-fileupload-1.2.1.jar	quartz-all-1.6.5.jar	xerces-2.6.2.jar
antlr.jar	commons-io-1.4.jar	rhino-1.7R1.jar	xercesImpl-2.7.0.jar
ant-swing-1.6.5.jar	commons-javaflow-20060411.jar	rome-0.5.jar	xml-apis-ext.jar
aopalliance-1.0.jar	commons-lang-2.4.jar	rome-fetcher-1.0.0.jar	xml-apis.jar
apache-log4j-extras-1.0.jar	commons-logging-1.1.1.jar	saaj-api-1.3.jar
apache-log4j-extras-1.1.jar	commons-pool-1.5.3.jar	servlet.jar
asm-attrs.jar	commons-validator.jar	slf4j-api-1.7.2.jar
asm.jar	concurrent-1.3.2.jar	slf4j-log4j12-1.7.2.jar
aspectjrt-1.6.8.jar	connector.jar	sojo-optional-0.5.0.jar
aspectjweaver-1.6.8.jar	dom4j-1.6.1.jar	spring-amqp-1.1.2.RELEASE.jar
barbecue-1.5-beta1.jar	ehcache-1.1.jar	spring-aop-3.0.1.RELEASE.jar
barcode4j-2.0.jar	flexjson.jar	spring-asm-3.0.1.RELEASE.jar
batik-anim.jar	google-collect-1.0.jar	spring-beans-3.0.1.RELEASE.jar
batik-awt-util.jar	groovy-all-1.5.5.jar	spring-context-3.0.1.RELEASE.jar
batik-bridge.jar	hibernate3.jar	spring-context-support-3.0.1.RELEASE.jar
batik-css.jar	hsqldb-1.8.0-10.jar	spring-core-3.0.1.RELEASE.jar
batik-dom.jar	iText-2.1.7.jar	spring-dao.jar
batik-ext.jar	jaas.jar	spring-expression-3.0.1.RELEASE.jar
batik-gvt.jar	jacc-1_0-fr.jar	spring-hibernate.jar
batik-parser.jar	jakarta-oro.jar	spring.jar
batik-script.jar	jasperreports-4.5.0.jar	spring-jdbc-3.0.1.RELEASE.jar
batik-svg-dom.jar	jasypt-1.2.jar	spring-jms.jar
batik-svggen.jar	jaxen-1.1.1.jar	spring-json-1.3.0.jar
batik-util.jar	jboss-cache.jar	spring-mock.jar
batik-xml.jar	jboss-common.jar	spring-orm.jar
bcel-5.2.jar	jboss-jmx.jar	spring-rabbit-1.1.2.RELEASE.jar
bsh-2.0b4.jar	jboss-system.jar	spring-remoting.jar
c3p0-0.9.0.jar	jcommon-1.0.15.jar	spring-security-acl-3.0.2.RELEASE.jar
camel-core-2.9.0.jar	jdbc2_0-stdext.jar	spring-security-config-3.0.2.RELEASE.jar
jta.jar	jdom-1.1.jar	spring-security-core-3.0.2.RELEASE.jar
junit-3.8.1.jar	jdt-compiler-3.1.1.jar	spring-security-web-3.0.2.RELEASE.jar
jxl-2.6.jar	jfreechart-1.0.12.jar	spring-support.jar
log4j-1.2.15.jar	jgroups-2.2.8.jar	spring-test.jar
log4j-1.2.16.jar	jpa.jar	spring-tx-3.0.1.RELEASE.jar
log4j-1.2.17.jar	json-lib-2.2.3-jdk15.jar	spring-web-3.0.1.RELEASE.jar
lucene-1.4.3.jar	jstl-1.1.2.jar	spring-webmvc-3.0.1.RELEASE.jar