## Project Plan
Project | Vbooks
Project Id | VT0001
Phases | TaskName | start | Finish | Duration | Resource names
Requirements Analysis |  | 2013-02-18 | 2013-03-15 | 20
Requirements Analysis | Analyse the Employee creation process | 2013-02-18 | 2013-02-19 | 2 | Sarath
Requirements Analysis | Analyse the Organisation creation process | 2013-02-20 | 2013-02-21 | 2 | Sarath
Requirements Analysis | Analyse the Accounts process | 2013-02-22 | 2013-02-26 | 2 | sarath
Requirements Analysis | Analyse the Sales process | 2013-02-27 | 2013-03-01 | 2 | Sarath
Requirements Analysis | Analyse the products process | 2013-03-04 | 2013-03-06 | 2 | Sarath
Requirements Analysis | Requirements Review | 2013-03-07 | 2013-03-11 | 2 | Sarath
Requirements Analysis | Include Feedback | 2013-03-12 | 2013-03-13 | 2 | Sarath
Requirements Analysis | Requirement Sign off | 2013-03-14 | 2013-03-15 | 2 | Sarath
Design |  | 2013-03-18 | 2013-06-21 | 70 days
Design | Detail Design of Employee module | 2013-03-18 | 2013-03-29 | 10 days | Ankit
Design | Detail Design of organisation module | 2013-04-01 | 2013-04-12 | 10 days | Priyanka
Design | Detail Design of Accounts module | 2013-04-15 | 2013-04-26 | 10 days | Vinay
Design | Detail Design of Sales module | 2013-04-29 | 2013-05-10 | 10 days | sudhakar/swarua
Design | Design Review | 2013-05-13 | 2013-05-24 | 10 days | Sateesh T
Design | DesignFeedback | 2013-05-27 | 2013-06-07 | 10 days | Sateesh T
Design | Design Sign off | 2013-06-10 | 2013-06-21 | 10 days | Sateesh T
Construction |  | 2013-06-24 | 2013-09-13 | 60 days
Construction | Code and Unit Test of Employee module | 2013-06-24 | 2013-07-05 | 10 days | Ankit
Construction | Code and Unit Test of organisation module | 2013-07-08 | 2013-07-19 | 10 days | Priyanka
Construction | Code and Unit Test of Accounts module | 2013-07-22 | 2013-08-02 | 10 days | Vinay
Construction | Code and Unit Test of Sales module | 2013-08-05 | 2013-08-16 | 10 days | sudhakar/swarua
Construction | Code Review | 2013-08-19 | 2013-08-30 | 10 days | Jaipal
Construction | Implement review changes | 2013-09-02 | 2013-09-13 | 10 days | Team
Verification |  | 2013-09-16 | 2013-11-15 | 45 days
Verification | prepare functional test plan | 2013-09-16 | 2013-09-20 | 5 days | Shahid
Verification | PrepareTest case scenarios | 2013-09-23 | 2013-10-04 | 10 days | Shahid
Verification | Prepare Test cases for each scenario | 2013-10-07 | 2013-10-11 | 5 days | Shahid
Verification | Integration Testing | 2013-10-14 | 2013-10-25 | 10 days | Shahid
Verification | Rebuild with Fixes | 2013-10-28 | 2013-11-08 | 10 days | Nageswar
Verification | Prepare Deployment Plan | 2013-11-11 | 2013-11-15 | 5 days | Sarath
Deployment |  | 2013-11-18 | 2014-02-14 | 22 days
Deployment | Deploy in UAT | 2013-11-18 | 2013-11-19 | 2 days | Sarath
Deployment | User Acceptance Test | 2013-11-20 | 2014-01-31 | 10 days | Sarath/Shahid
Deployment | Deploy in Production | 2014-02-03 | 2013-02-07 | 5 days | Sarath
Deployment | Sign off | 2014-02-10 | 2014-02-14 | 5 days | Client