## Project Plan
Project | Vbooks
Project Id | VT0001
Phases | TaskName | Plan start Date | Plan Finish Date | Actual start Date | Actual Finish Date | Plan Duration (Days) | Actual Duration(Days) | Resource names | Remarks
Requirements Analysis |  | 2013-02-18 | 2013-03-15 | 2013-02-18 | 2013-03-19 | 16 | 18
Requirements Analysis | Analyse the Employee creation process | 2013-02-18 | 2013-02-19 | 2013-02-18 | 2013-02-19 | 2 | 2 | Sarath
Requirements Analysis | Analyse the Organisation creation process | 2013-02-20 | 2013-02-21 | 2013-02-20 | 2013-02-21 | 2 | 2 | Sarath
Requirements Analysis | Analyse the Accounts process | 2013-02-22 | 2013-02-26 | 2013-02-22 | 2013-02-26 | 2 | 2 | sarath
Requirements Analysis | Analyse the Sales process | 2013-02-27 | 2013-03-01 | 2013-02-27 | 2013-03-05 | 2 | 4 | Sarath
Requirements Analysis | Analyse the products process | 2013-03-04 | 2013-03-06 | 2013-03-06 | 2013-03-08 | 2 | 2 | Sarath
Requirements Analysis | Requirements Review | 2013-03-07 | 2013-03-11 | 2013-03-11 | 2013-03-13 | 2 | 2 | Sarath
Requirements Analysis | Include Feedback | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2 | 2 | Sarath
Requirements Analysis | Requirement Sign off | 2013-03-14 | 2013-03-15 | 2013-03-18 | 2013-03-19 | 2 | 2 | Sarath
Design |  | 2013-03-18 | 2013-06-25 | 2013-03-20 | 2013-07-01 | 70 | 72 |  | Variation in the Actual Effort vs Planned is because of the change in the expected functionality in Sales modules
Design | Detail Design of Employee module | 2013-03-18 | 2013-04-01 | 2013-03-20 | 2013-04-03 | 10 | 10 | Ankit
Design | Detail Design of organisation module | 2013-04-02 | 2013-04-16 | 2013-04-04 | 2013-04-18 | 10 | 10 | Priyanka
Design | Detail Design of Accounts module | 2013-04-17 | 2013-04-30 | 2013-04-19 | 2013-05-02 | 10 | 10 | Vinay
Design | Detail Design of Sales module | 2013-05-01 | 2013-05-14 | 2013-05-03 | 2013-05-20 | 10 | 12 | sudhakar/swarua
Design | Design Review | 2013-05-15 | 2013-05-28 | 2013-05-21 | 2013-06-03 | 10 | 10 | Sateesh T
Design | DesignFeedback | 2013-05-29 | 2013-06-11 | 2013-06-04 | 2013-06-17 | 10 | 10 | Sateesh T
Design | Design Sign off | 2013-06-12 | 2013-06-25 | 2013-06-18 | 2013-07-01 | 10 | 10 | Sateesh T
Construction |  | 2013-06-26 | 2013-09-23 | 2013-07-02 | 2013-10-01 | 60 | 63 |  | Variation in the Actual Effort vs Planned is because of the change in the expected functionality in Sales modules
Construction | Code and Unit Test of Employee module | 2013-06-26 | 2013-07-09 | 2013-07-02 | 2013-07-15 | 10 | 10 | Ankit
Construction | Code and Unit Test of organisation module | 2013-07-10 | 2013-07-23 | 2013-07-16 | 2013-07-29 | 10 | 10 | Priyanka
Construction | Code and Unit Test of Accounts module | 2013-07-24 | 2013-08-06 | 2013-07-30 | 2013-08-14 | 10 | 11 | Vinay
Construction | Code and Unit Test of Sales module | 2013-08-07 | 2013-08-23 | 2013-08-16 | 2013-09-02 | 10 | 12 | sudhakar/swarua
Construction | Code Review | 2013-08-26 | 2013-09-06 | 2013-09-03 | 2013-09-17 | 10 | 10 | Jaipal
Construction | Implement review changes | 2013-09-10 | 2013-09-23 | 2013-09-18 | 2013-10-01 | 10 | 10 | Team
Verification |  | 2013-09-24 | 2013-11-29 | 2013-10-03 | 2013-12-09 | 45 | 46 |  | Variation in the Actual Effort vs Planned is because of the change in the expected functionality in Sales modules
Verification | prepare functional test plan | 2013-09-24 | 2013-09-30 | 2013-10-03 | 2013-10-10 | 5 | 5 | Shahid
Verification | PrepareTest case scenarios | 2013-10-01 | 2013-10-16 | 2013-10-11 | 2013-10-25 | 10 | 10 | Shahid
Verification | Functional Test Case Execution | 2013-10-17 | 2013-10-23 | 2013-10-28 | 2013-11-01 | 5 | 5 | Shahid
Verification | Integration Testing | 2013-10-24 | 2013-11-08 | 2013-11-04 | 2013-11-15 | 10 | 10 | Shahid
Verification | Rebuild with Fixes | 2013-11-11 | 2013-11-22 | 2013-11-18 | 2013-11-29 | 10 | 10 | Nageswar
Verification | Prepare Deployment Plan | 2013-11-25 | 2013-11-29 | 2013-12-02 | 2013-12-09 | 5 | 6 | Sarath
Deployment |  | 2013-11-30 | 2014-02-14 | 2013-12-10 | 2014-02-14 | 22 | 22 |  | Variation in the Actual Effort vs Planned is because of the change in the expected functionality in Sales modules
Deployment | Deploy in UAT | 2013-11-30 | 2013-12-03 | 2013-12-10 | 2013-12-11 | 2 | 2 | Sarath
Deployment | User Acceptance Test | 2013-12-04 | 2013-12-17 | 2013-12-12 | 2013-12-26 | 10 | 10 | Sarath/Shahid
Deployment | Deploy in Production | 2014-02-03 | 2013-02-07 | 2014-02-03 | 2013-02-07 | 5 | 5 | Sarath
Deployment | Sign off | 2014-02-10 | 2014-02-14 | 2014-02-10 | 2014-02-14 | 5 | 5 | Client
Post Production Support
Post Production Support | Support Activities | 2013-11-30 | 2014-08-29 | 2013-12-10 | 2014-08-29
Variation of Planned vs Actual Dates
Schedule variance Project | [5 empty] | 213 | 221 | 8 | 3.7559